Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 31/10/25 |
| --- | --- |
| Team ID | NM2025TMID08439 |
| Project Name | Optimization User, group and role management with access control and workflow |
| Maximum marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

Use the below template to create the product back

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint1 | User Management | USR-1 | As an admin, I can create and update user profiles for access control. | 2 | High | K.Yogita |
| Sprint1 | Group Management | USR-2 | As an admin, I can create groups and assign users to them for permission management. | 2 | High | S.Vinitha |
| Sprint 2 | Role Management | USR-3 | As a system admin, I can define roles and assign access rights to specific groups. | 3 | High | R.Suhashini |
| Sprint 2 | Access Control | USR-4 | As a security officer, I can enforce role based access control policies across workflows. | 3 | High | S.Swetha |
| Sprint 3 | Workflow Automation | USR-5 | As an admin, I can create approval workflows for user and role requests. | 3 | Medium | K.Yogita |
| Sprint 3 | Testing & Validation | USR-6 | As a QA engineer, I can test all modules and verify workflow and permission integrity. | 2 | Medium | S.Vinitha |
| Sprint 4 | Documentation | USR-7 | As a project member, We prepare technical and user documentation for the system. | 2 | Low | All Members |

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint start Date | Expected End date | Story Points completed | Actual End Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | 5/10/25 | 11/10/25 | 10 | 11/10/25 |
| Sprint-2 | 10 | 6 Days | 12/10/25 | 18/10/25 | 10 | 17/10/25 |
| Sprint-3 | 10 | 6 Days | 18/10/25 | 24/10/25 | 10 | 24/10/25 |
| Sprint-4 | 10 | 6 Days | 24/10/25 | 30/10/25 | 10 | 30/10/25 |

Velocity Calculation

Average Velocity = (Total Story Points Completed) / (Total Duration in Days) Total = 40 Story Points / 24 Days

Velocity = 1.67 points/day

Burndown Chart

A burndown chart is a graphical representation of work left to do versus time. It helps visualize progress and identify whether the team is on track to complete sprint goals.  References

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/ https://www.atlassian.com/agile/tutorials/burndown-charts https://www.atlassian.com/agile/project-management https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software https://www.atlassian.com/agile/tutorials/epics https://www.atlassian.com/agile/tutorials/sprints https://www.atlassian.com/agile/project-management/estimation